## Strategic planning
Group A Mythinati Gantt Chart
Activity | Assigned to | Week 1 (2/3 - 2/9) | [6 empty] | Week 2 (2/10 - 2/16) | [6 empty] | Week 3 (2/17 - 2/23) | [6 empty] | Week 4 (2/24 - 3/1) | [6 empty] | Week 5 (3/2 - 3/8) | [6 empty] | Week 6 (3/9-3/15) | [6 empty] | Week 7 (3/16-3/22) | [6 empty] | Week 8 (3/23-3/29) | [6 empty] | Week 9 (3/30-4/5) | [6 empty] | Week 10 (4/6 - 4/12) | [6 empty] | Week 11 (4/13 - 4/19) | [6 empty] | Week 12 (4/20 - 4/26) | [6 empty] | Week 13 (4/27 - 5/3) | [6 empty] | Week 14 (5/4 - 5/10) | [6 empty] | Week 15 (5/11-5/17)
|  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Start Project | Developers
Create vision document
Start Planning | Developers
Complete project plan document
Complete other documents
Start Execution
Necessary documents reviewed and approved
Resources for Unity and Photon Servers Committed
Confirm Execution
Design for gameplay functions approved
Design for gameplay rules approved
Start Introduction
Programming for gameplay functions
Programming for gameplay rules
Document programs included in high priority tasks
Release Product
Base product tested
Base product reviewed by involved stakeholders
1
Create vision document
0
Necessary documents reviewed and approved
Resources for Unity and Photon servers committed
Complete other documents
Complete project plan document
2
4
Programming for Gameplay functions finished
Programing for gameplay rules finished
3
Complete other documents
Complete project plan document
Documentation for high priority tasks done
Base Product tested by involved stakeholders
Base product reviewed by involved stakeholders
5
6
Close Project